Vision 2030 Committee Meeting
Date: June 16, 2025 at 7 pm @ Grimshaw Town Office 
Attendees: Brian Allen, Tanya Allen, Rose Estabrook, Colleen Sklapsky, Misty Velichka, Chance Gerk, Colette Robinson, Stacey Messner, Vanessa Burns
Regrets: Lucien Dubois, Tracy Halerewich

### 1. Welcome & Introductions

Brian Allen opened the meeting, welcoming committee members and providing a brief overview of the purpose of the committee.

### 2. Vision 2030 Event Planning

2.1. Event Concepts & Format

- Group agreed on hosting multiple events throughout the year, possibly quarterly.

- A major three-day “homecoming/reunion” event is envisioned for July 5–7, 2030, featuring a concert and/orlarge meal.

- Possibility of tying into existing events was raised.

- Kick-off event proposed to be the Canada Day Parade, possibly theming it to be the “Dirty Thirties” parade.

- Misty will take back the suggestion to the Harvest Moon committee about incorporating centennial activities into their fall event.

2.2. Involvement of Community & Non-Profits

- Non-profit groups will be invited to host or coordinate events or initiatives throughout the year.

- A Hall of Fame initiative will invite residents to nominate individuals for notable accomplishments.

2.3. Ambassadors & Event Hub

- Committee discussed appointing event ambassadors for the event.

- Suggested using Kennedy Gym as a central hub for the celebration:

  - Schedule of events

  - Hall of Fame display

  - Video viewings

  - Free coffee/snacks

### 3. Funding & Resources

- Misty shared information on grant funding opportunities for anniversary events, some up to $200,000, that need to be applied for the year before the event. Letters of support will be requested from community organizations.

- Consensus reached to offer a mix of free and ticketed events.

- Town Council currently has approximately $20,000 put aside for the celebration.

### 4. Golden Oldies Video Project

- A videographer will be hired to capture stories from Grimshaw’s senior residents.

- Colette Robinson will help identify interviewees.

- Kelsey from White Lightning was suggested for video production.

- Goal is to start this project soon in order to capture stories from seniors

### 5. Branding & Design

- Grimshaw 100th birthday branding may include concepts such as:

  - Grain elevators (including old wooden ones)

  - Train station

  - Grimshaw logo

  - Monument elements

- Colette will send photos to Vanessa for design inspiration.

- Vanessa will forward materials to Riley at Conveys (Peace River) and circulate proposed designs to the committee via email.

### 6. Action Items & Next Steps

- Send minutes to CAO Brian Allen for inclusion in upcoming Council meeting package.

- CAO to submit funding request to Council to release some funds for branding/videos

- Move forward with logo/branding (photos, design mockups) - Vanessa to contact Ryley at Conveys Marketing.

- Vanessa to send out calendar invite for next meeting:

  - Date: October 6, 2025

  - Time: 7:00 p.m.

- Vanessa to put out a public call for people to submit notable achievements/people in Grimshaw to start gathering information for the Hall of Fame portion of the celebration.

- Get a list of potential seniors (from Colette) for Golden Oldie videos.

- Contact Kelsey at White Lighting to discuss process/next steps.

### 7. Next Committee Meeting

Date: October 6, 2025 at 7 pm @ Grimshaw Town Office
Agenda Items:

- Appoint Committee Chair, Vice Chair, and Financial Coordinator

- Review branding and design progress

- Discuss Golden Oldies videos

- Review new ideas submitted

Note:
Colette Robinson volunteered to lead a History Committee